## 12345
| Description | [7 empty] | Fill these numbers in at the very start of the job (these are the original budgets for your furture reference) |  | These numbers are fed from the 'guts' of your spread sheet and will change as you alter the numbers. This may be due to changes in labour or quotes coming in | These are the actual numbers based on the WiP data (see 'Hours/Costs to Date' table below/left) | These numbers are the difference between the ongoing budget and the Actual budget
Spine wall by others
Ongoing Budget
| Labour |  |  | Rate | Hours | Days | Value | % Sale | Original Budget |  | Ongoing Budget | Actual to Date | £ DIFF
man | Management |  |  | 18 | 0 | 0 | 0 | 0% | 0 |  | 0 | 0 | 0 | Management
dwg | Drawing |  |  | 18 | 0 | 0 | 0 | 0% | 0 |  | 0 | 0 | 0 | Drawing
mfg | Manufacturing |  |  | 15 | 0 | 0 | 0 | 0% | 0 |  | 0 | 0 | 0 | Manufacturing
fin | Finishing |  |  | 15 | 0 | 0 | 0 | 0% | 0 |  | 0 | 0 | 0 | Finishing
pdf | Pack, Delivery & Fiitting |  |  | 15 | 0 | 0 | 0 | 0% | 0 |  | 0 | 0 | 0 | Pack, Delivery & Fitting
| labour Total |  |  |  | 0 | 0 | 0 | 0% | 0 |  | 0 | 0 | 0 | Labour Total
Materials
| Transport & Storage |  | mile rate | 0.5 |  |  | 0 | 0% | 0 |  | 0 | 0 | 0 | Transport & Storage
| External | [5 empty] | 0 | 0% | 0 |  | 0 | 0 | 0 | External
| Materials | [5 empty] | 0 | 0% | 0 |  | 0 | 0 | 0 | Materials
| Materials Total | [5 empty] | 0 | 0% | 0 |  | 0 | 0 | 0 | Materials Total
| labour + Materials total | [5 empty] | 0 | 0% | 0 |  | 0 | 0 | 0 | labour + Materials total
| Contingency (percentage of labour +materials) |  | Rate | 5% |  |  | 0 | 0% | 0 |  | 0 | 0 | 0 | Contingency
| Labour + Materials + contingency total | [5 empty] | 0 | 0% | 0 |  | 0 | 0 | 0 | Lab + Mats + Cont Total
| Overheads |  | Rate | 30% |  |  | 10335 | 30% | 0 |  | 10335 | 10335 | 0 | Overheads
| Actual cost ( Labour + materials +contingency + overheads ) | [5 empty] | 10335 | 30% | 0 |  | 10335 | 10335 | 0 | Actual cost
Contractor Disc
| Quote Price |  | margin test example | 15% | 0 |  | 34450 | 0% | 0 |  | 34450 | 34450 | 0 | Quote Price
| Per Rise |  |  |  | No. of rises: | 14 | 2460.7143
[9 empty] | £ Original Margin |  | £ Ongoing Margin | £ Actual margin
| MARGIN | [5 empty] | 24115 | 70% | 0 |  | 24115 | 24115 | 0 | Margin
| Margin and contingency | [5 empty] | 24115 | 70% | #DIV/0! |  | 70% | 70%
HOURS/ COSTS TO DATE
|  |  | Hours | Hours | Value | Value | % hours | % value
| Labour | (was LAB to split up) |  | Remain |  | Remain | used | used
| Management | MAN | 0 | 0 | 0 | 0
| Drawing | DWG | 0 | 0 | 0 | 0
| Manufacturing | MFG | 0 | 0 | 0 | 0
| Finishing | FIN | 0 | 0 | 0 | 0
| Pack Delivery Fit | PDF | 0 | 0 | 0 | 0
| Labour Total |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Other
| Transport & Storage | TTS (was OHD) |  |  | 0 | 0
| External Costs/Subcontractors | EXT |  |  | 0 | 0
| Materials | MAT |  |  | 0 | 0
| Materials Total |  |  |  | 0 | 0 |  | #DIV/0! | 32%
|  |  |  | check total | 0
JOB COSTS
Ref | MANAGEMENT LABOUR |  | Qty | Hours | Tot Hrs | Rate | Cost
| Management Time |  | 0 | 0
| Method statement |  |  | 1
| hazardous chemicals |  |  | 1
| Health and Safety Doc's |  |  | 1
| misc red tape |  |  | 1
| Messing with Engineer |  |  | 8
| Total Management Costs |  |  |  | 0 |  | 0
Ref | DRAWING LABOUR |  | Qty | Hours | Tot Hrs | Rate | Cost
| Drawing Time | Preliminary | 0 | 8
| Drawing Time | Ammendments | 0 | 8
| Drawing Time | Construction | 0 | 8
| Draw CNC bits |  | 0 | 8
| Total Drawing Costs |  |  |  | 0 |  | 0
Ref | MANUFACTURING LABOUR |  | Qty | Hours | Tot Hrs | Rate | Cost
| cnc | stringers | 0 | 8
| Glue up stringers |  | 0 | 8
| treads | tread/rise | 0 | 4
| Soffit | None
| Shaped Landing top | nosing | 0 | 8
| handrail | check over | 0 | 8
| spine wall | inc return |  | 8
| top nosing tread |  | 0 | 6
| Cutting studs | tread to wall fix | 0 | 8
| Total Manufacturing Costs |  |  |  | 0 |  | 0
Ref | FINISHING LABOUR |  | Qty | Hours | Tot Hrs | Rate | Cost
| Treads/Riser |  | 0 | 8
| General sanding cleaning |  | 0 | 8
| Wall |  |  | 8
| Total Finishing Labour Costs |  |  |  | 0 |  | 0
Ref | PACK, DELIVERY & FITTING LABOUR |  | Qty | Hours | Tot Hrs | Rate | Cost
| pack and load |  | 0 | 4 | 0 | 15 | 0 |  | days | hours
[9 empty] | 2 | 16
| measure up/handover | 2 men 1 day | 0 | 8 | 0 | 15 | 0 |  | 3 | 24
| Wall frame | 2 men 1 day |  | 8 | 0 | 15 | 0 |  | 6 | 48
| wall cladding | 2 men 2 days |  | 16 | 0 | 15 | 0 |  | 7 | 56
| outer tread supports | 2 men 1 day | 0 | 8 | 0 | 15 | 0 |  | 8 | 64
| inner tread supports | 2 men 1 day | 0 | 8 | 0 | 15 | 0 |  | 9 | 72
| tread substrates | 2 men 1 day | 0 | 8 | 0 | 15 | 0 |  | 10 | 80
| tread tops | 2 men 2 days | 0 | 16 | 0 | 15 | 0
| handrail | 1 man 1 day | 0 | 8 | 0 | 15 | 0
| Misc | 1 men 1 day | 0 | 8 | 0 | 15 | 0
Ref | SURVEY/MEETING |  | Qty | Hours | Tot Hrs | Rate | Cost
| Site Survey |  | 0 | 2
| Meetings |  | 0 | 1
| Total Pack, Delivery and Fitting Costs |  |  |  | 0 |  | 0
TOTAL LABOUR TIME AND COSTS |  |  |  |  | 0 |  | 0
Ref | TRANSPORT & STORAGE |  | Qty | Rate |  |  | Cost
| Travel (5hrs/man/day) | (G213/8X5)x15 | 0 | 15 | Calculated automatically |  | 0
| Subsidance |  | 0 | 6 | Calculated automatically |  | 0
| Mileage |  | 0 | 0.5 |  |  | 0
| Vehicle Hire | Days |  | 240 |  |  | 0
| Deliveries (City Sprint) |  | 0 | 400 |  |  | 0
| Haulage |  |  | 1 |  |  | 0
| External Storage |  |  | 1 |  |  | 0
| ferry |  |  | 1 |  |  | 0
| train tickets | £100/week/man | 0 | 350 |  |  | 0
| train tickets | surveys | 0 | 40 |  |  | 0
| Congestion Charge | £10 per day | 0 | 10 |  |  | 0
| Total Transport Costs | [5 empty] | 0
Ref | EXTERNAL COSTS |  | Qty | Rate |  |  | Cost
| JP Fabrication | Rolled angles | 0 | 800 |  |  | 0
|  | inner saw tooth |  | 1000 |  |  | 0
|  | tread plates |  | 3 |  |  | 0
|  | spiggots |  | 5 |  |  | 0
|  | bushes |  | 2 |  |  | 0
|  | General fixings |  | 200 |  |  | 0
| Powder Coating | outer stringers |  | 250 |  |  | 0
|  | inner saw tooth |  | 400 |  |  | 0
|  | balusters |  | 5 |  |  | 0
|  | links |  | 3 |  |  | 0
|  | washers |  | 1 |  |  | 0
| Leather Handrail |  | Length | Hides
| Hide (14LinM of handrail) |  |  |  | (1 No. hide = £ 550) |  | 0
| Fitting £240/m) | tucking in rebate |  | 240 |  |  | 0
|  | twin & cross stitch |  | 300 |  |  | 0
| Handrail curve |  |  | 620 |  |  | 0
| Handrail straight |  |  | 250 |  |  | 0
| brass brackets |  |  | 60 |  |  | 0
| Total Miscellaneous Costs | [5 empty] | 0
| Timber |  | Qty | Unit |  | Value | Cost
| Merbau wood | over estimated | 0 | 3000 |  | 0
| veneer for spine wall | under estimated |  | 200 |  | 0 |  |  | Ply = £2.0391/mm
| 29mm Oak | 2030x2100 |  | 436 |  | 0
|  | 2030x2400 |  | 520 |  | 0 |  |  | Thickness mm | 0 |  | 2.0391 | 0
| 40mm Oak | 2030x2100 |  | 436 |  | 0
|  | 2030x2400 |  | 520 |  | 0
W | Tread tops | triply |  | 360 |  | 0
O | treads | Cork | 0 | 20 |  | 0
O | tread substrate | ply | 0 | 42 |  | 0
| timber studs | spine wall | 0 | 150 |  | 0
D | machined | all |  | 19 |  | 0
| corian glue |  |  | 300 |  | 0
| ply | soffit substrate |  | 20 |  | 0
| Handrail | Straight £38/m |  | 38 |  | 0
| Handrail |  | 0 | 1750 |  | 0
| Capping | Larch 2030x4000 |  | 380 |  | 0
| Soffits | pre-veneered |  | 25 |  | 0
| Composite Tread Core | Kerto |  | 40 |  | 0
| Landing Soffit | pre veneered |  | 25 |  | 0
| Balustrade | MDF 2440x1220 |  | 25 |  | 0
| Softwood |  |  | 100 |  | 0
| Treads | substrate |  | 22 |  | 0
| Landing | 19 Oak Triply 2030x2100 |  | 400 |  | 0
| Fascia | pre-veneered |  | 25 |  | 0
| Capping top/btm balustrade | MDF 2440x1220 |  | 25 |  | 0
| Stringer | ply stringers | 0 | 200 |  | 0
| Stringer Cladding | veneer |  | 150 |  | 0
| Stringer Cladding MDF |  |  | 25 |  | 0
| Handrail | softwood core |  | 100 |  | 0
| cork | 2m req @ £50/m |  | 50 |  | 0
| Fascia | pre veneered |  | 50 |  | 0
| Veneer | £25/m2 (£25/tread) |  | 26 |  | 0
0
G | 17.5mm Lam |  | 0 | 600 |  | 0
L
A | 12mm toughen'd
S
S | 15mm Toughen'd
Glass General
0
| Flor fixings |  | 0 | 400 |  | 0
| general |  | 0 | 50 |  | 0
| Laser cutting | tread plates |  | 3.5 |  | 0
| Laser cutting | washers |  | 0.75 |  | 0
M | Laser cutting | tread inner ends |  | 8 |  | 0
E | laser cutting | top cap |  | 10 |  | 0
T | Laser cutting | landing tray |  | 40 |  | 0
A | Laser cutting | tread ends |  | 20 |  | 0
L | laser cutting | base/top fixing |  | 20 |  | 0
| laser cutting | glass clamps |  | 150 |  | 0
| Nosing support | angle? |  | 15 |  | 0
| Centre Pole | 2 No. required |  | 900 |  | 0
| hanging junction boxes |  |  | 25 |  | 0
| cable |  |  | 200 |  | 0
| lindapter things | Girder clamps prices tbc |  | 30 |  | 0
| balusters | 19mm dia |  | 500 |  | 0
| handrail | tube £90/m |  | 90 |  | 0
| handrail bracket |  |  | 12 |  | 0
| Handrail | terminations |  | 15 |  | 0
| handrail substrate sections |  |  | 1000 |  | 0
| Glass clamp | top landing closing rail |  | 100 |  | 0
| Polishing | £100/m |  | 1000 |  | 0
| Polishing Supports | £40 per tread |  | 40 |  | 0
| Final Polishing (After weld) |  |  | 750 |  | 0
| All other angles by JP |  |  | 450 |  | 0
| Capping infills | Stainless Steel |  | 300 |  | 0
| Base Plate | Mild Steel |  | 30 |  | 0
| top fix Structure | landing frame |  | 300 |  | 0
| Tread Supports | Design unknown |  | 20 |  | 0
| Base Plate |  |  | 20 |  | 0
| Sockets |  |  | 3.5 |  | 0
| Handrail terminations |  |  | 10 |  | 0
| Studs | 12mm |  | 0.8 |  | 0
| General fixings |  |  | 50 |  | 0
| Studs | 16mm |  | 0.9 |  | 0
| curved aluminium track | base of glass |  | 25 |  | 0
| Handrail Brackets | Complete item |  | 25 |  | 0
| Washers |  |  | 2.5 |  | 0
| Spacers |  |  | 2.5 |  | 0
| Laser cutting | stringers 8mm |  | 125 |  | 0
| Laser cutting | Fascias 8mm |  | 150 |  | 0
| CNC Pole |  |  | 500 |  | 0
Stainless Steel Handrail
| 42mm dia 304 slotted | 2.5m length £75/m |  | 75 |  | 0
| Rubber gaskett | 2.5m length £20/m |  | 20 |  | 0
| inline connector | Straight £11/e |  | 11 |  | 0
| 90° mitre |  |  | 22 |  | 0
| wall plate |  |  | 12 |  | 0
| end cap |  |  | 8.5 |  | 0
0
| mastic |  |  | 75 |  | 0
O | Epoxy Grout Thixotropic |  |  | 50 |  | 0
T | Glass paint |  |  | 40 |  | 0
H | Train Ticket |  |  | 25 |  | 0
E | Silicon |  |  | 25 |  | 0
R | Primer |  | 0 | 50 |  | 0
| Sundries |  | 0 | 20 |  | 0
| Laquer |  | 0 | 50 |  | 0
0
| Total Materials Costs | [5 empty] | 0