## Sheet1
Week
Tasks |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Research | bar: Week 1 to Week 3
Agree Project | bar: Week 2 to Week 3
Write Specification | bar: Week 3 to Week 4
Initial drawings | bar: Week 4 to Week 7
Choose design to develop | bar: Week 7
Model in materials and / or CAD | bar: Week 8 to Week 9
Record problems that need solving | bar: Week 7 to Week 9
Re-model to iron out issues | bar: Week 9 to Week 10
Change CAD design as needed | bar: Week 7 to Week 10
Create a production drawing (ortho) | bar: Week 11
Check off drawing with tutor / client | bar: Week 11
Create a production schedule | bar: Week 3 to Week 12
ABC costing and order materias | bar: Week 11 to Week 12
Create the project outcome | bar: Week 13 to Week 16
Evaluate against specification | bar: Week 5 to Week 18